## Gantt Chart
| Tasks | Start Date | End Date | Friday |  |  | Saturday |  |  | Sunday |  |  | Monday |  |  | Tuesday |  |  | Wednesday |  |  | Thursday |  |  | Team Members
1 | Planning | 04/062021 | 2021-06-06 | [21 empty] | Supreet kaur
1.1 | Look through the assessment |  |  | Group Work in class | [20 empty] | Amanpreet kaur
1.2 | Talk about the assessment | [23 empty] | Sahibjot Singh
1.3 | Discuss about the topic
1.4 | Start Research
|  | Total Hours | 84 | 8hr | 8hr | 8hr | 10hr | 10hr | 10hr | 10hr | 10hr | 10hr
2 | Recap | 2021-06-07 | 2021-06-13
2.1 | Give reviews about last week research | [17 empty] | Group work in class
2.2 | Conclusion
2.3 | Decide Topic
2.4 | Plan Layouts | [20 empty] | Group Work in class
2.5 | Start Making layouts |  |  | Group Work in class | [14 empty] | 4hr | 4hr | 4hr
2.6 | Research about backend coading (Watch youtube vedios) |  |  | 8hr | 8hr | 8hr |  | 10hr |  |  | 10hr |  |  | 10hr | [8 empty] | 8hr | 8hr
[7 empty] | 10hr |  | 10hr | 10hr |  | 10hr | 10hr |  | 10hr
|  | Total Hours | 150
3 | Front end, backend and testing | [15 empty] | 10hr
3.1 | Working on backend and testing | 2021-06-14 | 2021-06-20 | Group work in class | [14 empty] | Group work in class |  |  | Group work in class
3.2 | Working on layouts | [11 empty] | 10hr | 10hr |  | 10hr
|  |  |  | 8hr | 8hr | 8hr | [8 empty] | 10hr |  | 10hr |  | 4hr | 4hr | 4hr | 8hr | 8hr | 8hr
|  | Total hours | 120
|  | 2021-06-21 | 2021-06-27
4 | Database, Layouts and Activities And Testing
4.1 | working on database and testing |  |  | Group work in class
4.2 | working on layouts
4.3 | working on activities |  |  | 8hr | 8hr | 8hr
4.4 | working on layouts | [5 empty] | 10hr | 10hr |  | 10hr | 10hr |  | 10hr | 10hr |  | 10hr | 10hr
4.5 | Working on documentation | [13 empty] | 10hr |  |  | 10hr | Group work in class |  |  | Group work in class
|  | Total hours | 160
[19 empty] | 4hr | 4hr | 4hr | 8hr | 8hr | 8hr

## Team communication
Team Communication

## UI Prototype
Wireframes

## Daily Meetings
First Week
Start Date | 2021-06-04
End date | 2021-06-06 | Team Members | Questions | Wednesday | Thursday | Friday
|  | Supreet kaur | What did you do yesterday?
|  |  | What will you work on today? |  |  | Read Assessment
|  |  | Do You have any obstacles? |  |  | No Obstacles
|  | Amanpreet kaur | What did you do yesterday?
|  |  | What will you work on today? |  |  | Read Assessment
|  |  | Do You have any obstacles? |  |  | No Obstacles
|  | Sahibjot Singh | What did you do yesterday?
|  |  | What will you work on today? |  |  | Read Assessment
|  |  | Do You have any obstacles? |  |  | Face littlebit difficulty to understand the assessment but i will be able to understand after discussing with my team members
Second Week
Start Date | 2021-06-09
End Date | 2021-06-11 | Team Members | Questions | Wednesday | Thursday | Friday
|  | Supreet kaur | What did you do yesterday? | I read the assessment again at home and think about the topic and did some research | Me and my team decide our final topic | Worked on layouts
|  |  | What will you work on today? | Today i am going to discuss about the assesment topic and research which i did yesterday | Today i am going to start work on layouts with my team members | Start research on backend coading
|  |  | Do You have any obstacles? | I faced some difficulties in choosing topic but i solved after discussing my team members | No obstacles | Face some issues in backend research
|  | Amanpreet kaur | What did you do yesterday? | Think about the topic at home and did research | Decide Topic | Worked Layouts
|  |  | What will you work on today? | Today i am going to discuss about the assesment topic and research which i did yesterday | Working on layouts | Start research on backend
|  |  | Do You have any obstacles? | i faced some difficulties while doing research | No obstacles | Face some problems on backend research
|  | Sahibjot Singh | What did you do yesterday? | Did research at home | Doing research and decide topic | worked on layouts
|  |  | What will you work on today? | Discuss about the topic with team members | Start working on layouts | working on layouts
|  |  | Do You have any obstacles? | Face some issues in research | Face issues while making layouts | Face issues and discuss with team members
Third Week
Start Date | 2021-06-16
End Date | 2021-06-18 | Team Members | Question | Wednesday | Thursday | Friday
|  | Supreet kaur | What did you do yesterday? | Worked on Database | Worked on Database | Worked on Database
|  |  | What will you work on today? | Still work on Database | Working on Database | Working on Database
|  |  | Do You have any obstacles? | face some obstacles in some steps | face obstacles discuss with group members | face issues while doing coading discuss with group members
|  | Amanpreet kaur | What did you do yesterday? | Worked on Models and helped group members in their issues | Worked on Models and help group members | Worked on Models
|  |  | What will you work on today? | Working on Models | Working on Models and also helping sahibjot in layout part | Start Working on Activities
|  |  | Do You have any obstacles? | Face problems while doing coading on models | No issues faced | face some obstacles while doing activities
|  | Sahibjot Singh | What did you do yesterday? | Worked on layouts | Worked on layouts | Worked on layouts
|  |  | What will you work on today? | Working on layouts | Working on layouts and going to discuss about some steps with my group members | Working on layouts and start thinking about presentation
|  |  | Do You have any obstacles? | I faced many issues while desiging layout but I solved by discussing with my team members | No obstacles | No Issues
Fourth week
Start date | 2021-06-23
End date | 2021-06-25 | Team Members | Question | Wednesday | Thursday | Friday
|  | Supreet kaur | What did you do yesterday? | Worked on database | Worked on activities | Worked on activities and documentation
|  |  | What will you work on today? | Start working on activities | Still working on activities and start documentation | Working on activities and documentation
|  |  | Do you have any obstacles? | I faced some obstacles while making activities | face some issues discus with group members | No issues
|  | Amanpreet kaur | What did you do yesterday? | Worked on activities | worked on activities and documentation | Yesterday i worked on documentation
|  |  | What will you work on today? | Working on activities and documentation | I will work on documentation today | I will work on documentation
|  |  | Do you have any obstacles? | i faced some issues in activities | no issues | no issues
|  | Sahibjot Singh | What did you do yesterday? | Yesterday i worked on layouts | Yesterday i start the question answer part | Yesterday i compeleted the question answer part
|  |  | What will you work on today? | I will start the Question answer part | Today i will try to compelete the question answer part | today i will start the other documentation
|  |  | Do you have any obstacles? | I faced issues in finding the answers of questions | No issues | No issues

## Testing1
Agile Application Testing
Steps | Step Details | Expected results | Actual Results | Pass/Fail/Error
1 | Saplash activity page | Spalash activity (Sales Sharks)Displayed | Sales Sharks Image display | Pass
2 | All Items page | Options like category item,product item and sale iten should displayed | Options display | Pass
3 | Category items page | Add,Update,View.Remove Category options displyaed | All Options display | Pass
4 | Product items page | Add,Update,View.Remove Product options displyaed | All Options display | Pass
5 | Sale items page | Add,View,Remove sale options will displayed | All Options display | Pass
6 | Buttons | Buttons will clickable | Buttons are clickable | Pass
7 | Color Schema | Light blue and yellow with text black | Displayed | Pass
Responsiveness
| All Items Page |  |  |  | Category Items Page
| Product items page |  |  |  | Sale items page
Responsiveness
| App Pages | Errors | Pass/Fail/Error
| Page1 |  | Pass
| Page2 |  | Pass
| Page3 |  | Pass
| Page4 |  | Pass

## Testing2
Usability Testing
Usability and Acessability | Agree | Neutral | Disagree | Unsure | Comments
The app is load in android | Yes
Saplash activity page opens while run | Yes
The page is self explanatory and i know how to use it | Yes
Functionality
All the buttons work correctly | Yes
Crud Opreation | Yes
Can Add,Update,Remove and View as well | Yes
Readibility
The font are suitable and easy to read | Yes
The Size and style of the font is easy to read | Yes
The combination between text color and background looks easy to read | Yes
There is sufficient spacing to make the pages easy to read | Yes
Sales For Purpose
The application is suitable and fulfill its purpose | Yes
The application is suitable for the target audience | Yes